## Roadmap Overview
Internship Roadmap — "We" vs "Them" Language Analysis on Social Media
# | Week / Phase | Dates | Main Activities | Deliverable | Tools / Methods | Status
PHASE 1 · Data Acquisition & Preliminary Analysis (Weeks 1–2)
W1 | Week 1 | 13–17 Apr | • Set up Python env (PRAW, yt-dlp, HuggingFace Transformers) • Implement safe Reddit & YouTube scraping • Design metadata schema: post_id, platform, timestamp, engagement, text, language, toxicity_raw • Init Git repo + data dictionary | GitHub repo + data dictionary doc | Python, PRAW, yt-dlp, pandas | 🔄 In progress
W2 | Week 2 | 20–24 Apr | • Data cleaning: dedup, lang-detect (langdetect), null handling • Negativity × engagement correlation (Spearman ρ) • We/Them baseline: pronoun ratio + custom lexicon match • Time-of-day & reply-depth distribution plots | EDA notebook + baseline metrics report | pandas, scipy, matplotlib, seaborn | ⬜ Not started
PHASE 2 · Multimodal Analysis & Network Science (Weeks 3–5)
W3 | Week 3 | 27 Apr–1 May | • Prototype CLIP zero-shot pipeline (openai/clip-vit-base-patch32) • Compute image–text cosine similarity on Instagram subset • Label meme categories (in-group / out-group / neutral) • Evaluate alignment between visual & textual We/Them cues | CLIP eval report + labelled dataset | HuggingFace CLIP, PIL, scikit-learn | ⬜ Not started
W4 | Week 4 | 4–8 May | • Build hashtag co-occurrence matrix (window = 5 tokens) • Construct weighted undirected graph with NetworkX • Compute degree, betweenness centrality & PageRank • Run Louvain community detection → identify narrative clusters | Network visualisation + centrality stats CSV | NetworkX, python-louvain, pyvis | ⬜ Not started
W5 | Week 5 | 11–15 May | • Build directed reply/reshare interaction graphs • Detect echo chambers: modularity score + internal vs external density ratio • Merge cross-platform graphs (Reddit / YouTube / Instagram) • Map We/Them prevalence per detected community | Echo chamber analysis report + graph exports | NetworkX, igraph, gephi (optional) | ⬜ Not started
PHASE 3 · Linguistic Mapping & Dashboarding (Weeks 6–8)
W6 | Week 6 | 18–22 May | • Compute We/Them pronoun ratio per community/topic cluster • Score toxicity via Perspective API (attributeScores) • Generate cluster-level heatmaps • Calculate polarization index = We/Them ratio × mean toxicity | Annotated heatmaps + toxicity CSV | Perspective API, seaborn, plotly | ⬜ Not started
W7 | Week 7 | 25–29 May | • Build Streamlit app skeleton with sidebar filters (platform, date, topic) • Implement cross-platform comparison tab • Integrate network visualisation + toxicity charts (Plotly/Altair) • Add We/Them prevalence time-series tab | Live Streamlit app (localhost demo) | Streamlit, Plotly, Altair | ⬜ Not started
W8 | Week 8 | 1–5 Jun | • Produce final comparative tables: negativity, toxicity, topic density, engagement • QA dashboard: edge cases, mobile responsiveness, filter bugs • Mid-point supervisor review session • Incorporate feedback → v1.0 dashboard release | Reviewed dashboard v1.0 + QA log | Streamlit, Plotly, pytest | ⬜ Not started
PHASE 4 · Documentation & Reporting (Weeks 9–10)
W9 | Week 9 | 8–12 Jun | • Write Methods section (data pipeline, NLP pipeline, network methods) • Write Results & Findings (tables, plots, key numbers) • Document codebase (docstrings + README.md) • Document Streamlit architecture (data flow diagram) | Draft report (50%) + documented codebase | LaTeX / Word, Sphinx (optional) | ⬜ Not started
W10 | Week 10 | 15–19 Jun | • Complete Discussion, Limitations & Future Work sections • Structure research paper in IMRAD format • Prepare 10–12 slide defense presentation • Defense rehearsal with supervisor • Final submission of report + slides | Final report + presentation slides | PowerPoint / Beamer, Canva | ⬜ Not started

## Weekly Task Tracker
Weekly Task Tracker
Week | Task | Phase | Category | Priority | Status | % Done
W1 | Set up Python virtual environment | Phase 1 | Setup | High | 🔄 In progress | 🔄 In progress
W1 | Install PRAW, yt-dlp, HuggingFace libs | Phase 1 | Setup | High | 🔄 In progress | 🔄 In progress
W1 | Implement Reddit scraper (PRAW) | Phase 1 | Scraping | High | ⬜ Not started | ⬜ Not started
W1 | Implement YouTube scraper (yt-dlp) | Phase 1 | Scraping | High | ⬜ Not started | ⬜ Not started
W1 | Design metadata schema | Phase 1 | Data Design | High | ⬜ Not started | ⬜ Not started
W1 | Init Git repo + data dictionary | Phase 1 | Setup | Med | ⬜ Not started | ⬜ Not started
W2 | Data cleaning pipeline | Phase 1 | EDA | High | ⬜ Not started | ⬜ Not started
W2 | Spearman correlation: negativity × engagement | Phase 1 | Analysis | High | ⬜ Not started | ⬜ Not started
W2 | We/Them pronoun lexicon + baseline metrics | Phase 1 | NLP | High | ⬜ Not started | ⬜ Not started
W2 | Time-of-day & reply-depth plots | Phase 1 | Viz | Med | ⬜ Not started | ⬜ Not started
W3 | Set up CLIP pipeline | Phase 2 | Multimodal | High | ⬜ Not started | ⬜ Not started
W3 | Image-text cosine similarity on Instagram subset | Phase 2 | Multimodal | High | ⬜ Not started | ⬜ Not started
W3 | Meme labelling (in/out/neutral) | Phase 2 | Multimodal | Med | ⬜ Not started | ⬜ Not started
W4 | Build hashtag co-occurrence matrix | Phase 2 | Network | High | ⬜ Not started | ⬜ Not started
W4 | NetworkX graph + centrality metrics | Phase 2 | Network | High | ⬜ Not started | ⬜ Not started
W4 | Louvain community detection | Phase 2 | Network | High | ⬜ Not started | ⬜ Not started
W5 | Build reply/reshare directed graphs | Phase 2 | Network | High | ⬜ Not started | ⬜ Not started
W5 | Echo chamber detection (modularity) | Phase 2 | Network | High | ⬜ Not started | ⬜ Not started
W5 | Cross-platform graph merge | Phase 2 | Network | Med | ⬜ Not started | ⬜ Not started
W6 | We/Them ratio per community | Phase 3 | NLP | High | ⬜ Not started | ⬜ Not started
W6 | Perspective API toxicity scoring | Phase 3 | NLP | High | ⬜ Not started | ⬜ Not started
W6 | Cluster heatmaps + polarization index | Phase 3 | Viz | Med | ⬜ Not started | ⬜ Not started
W7 | Streamlit app skeleton + sidebar filters | Phase 3 | Dashboard | High | ⬜ Not started | ⬜ Not started
W7 | Cross-platform comparison tab | Phase 3 | Dashboard | High | ⬜ Not started | ⬜ Not started
W7 | Integrate network + toxicity charts | Phase 3 | Dashboard | High | ⬜ Not started | ⬜ Not started
W8 | Comparative tables (negativity/toxicity/topic density) | Phase 3 | Analysis | High | ⬜ Not started | ⬜ Not started
W8 | Dashboard QA + bug fixes | Phase 3 | Dashboard | High | ⬜ Not started | ⬜ Not started
W8 | Mid-point supervisor review | Phase 3 | Review | High | ⬜ Not started | ⬜ Not started
W9 | Write Methods section | Phase 4 | Report | High | ⬜ Not started | ⬜ Not started
W9 | Write Results & Findings | Phase 4 | Report | High | ⬜ Not started | ⬜ Not started
W9 | Code documentation + README | Phase 4 | Docs | Med | ⬜ Not started | ⬜ Not started
W10 | Write Discussion, Limits, Future Work | Phase 4 | Report | High | ⬜ Not started | ⬜ Not started
W10 | Prepare 10–12 slide defense presentation | Phase 4 | Slides | High | ⬜ Not started | ⬜ Not started
W10 | Defense rehearsal with supervisor | Phase 4 | Review | High | ⬜ Not started | ⬜ Not started
Total tasks |  |  |  |  | 0 | 0%